## Slide 1: Project Management
Project Controlling
Project Management Techniques: PERT And CPM
  The Framework Of PERT And CPM
  Network Diagrams And Approaches
  Activity-on-Node
  Activity-on-Arrow

## Slide 2: Project Management
Determining The Project Schedule
  Forward Pass
  Backward Pass
  Calculating Slack Time And Identifying The Critical Path(s)
Variability In Activity Times
  Three Time Estimates In PERT
  Probability Of Project Completion

## Slide 3: Management of Projects
Planning - goal setting, defining the project, team organization
Scheduling - relates people, money, and supplies to specific activities and activities to each other
Controlling - monitors resources, costs, quality, and budgets; revises plans and shifts resources to meet time and cost demands

## Slide 4: Project Scheduling
Identifying precedence relationships
Sequencing activities
Determining activity times & costs
Estimating material and worker requirements
Determining critical activities

## Slide 5: Project Management Techniques
Gantt chart
Critical Path Method (CPM)
Program Evaluation and Review Technique (PERT)

## Slide 6: A Simple Gantt Chart
Time
J F M A M J J A S
Design
Prototype
Test
Revise
Production

## Slide 7: PERT and CPM
Network techniques
Developed in 1950’s
  CPM by DuPont for chemical plants (1957)
  PERT by Booz, Allen & Hamilton with the U.S. Navy, for Polaris missile (1958)
Consider precedence relationships and interdependencies
Each uses a different estimate of activity times

## Slide 8: Six Steps PERT & CPM
Define the project and prepare the work breakdown structure
Develop relationships among the activities - decide which activities must precede and which must follow others
Draw the network connecting all of the activities

## Slide 9: Six Steps PERT & CPM
Assign time and/or cost estimates to each activity
Compute the longest time path through the network – this is called the critical path
Use the network to help plan, schedule, monitor, and control the project

## Slide 10: Questions PERT & CPM Can Answer
When will the entire project be completed?
What are the critical activities or tasks in the project?
Which are the noncritical activities?
What is the probability the project will be completed by a specific date?

## Slide 11: Questions PERT & CPM Can Answer
Is the project on schedule, behind schedule, or ahead of schedule?
Is the money spent equal to, less than, or greater than the budget?
Are there enough resources available to finish the project on time?
If the project must be finished in a shorter time, what is the way to accomplish this at least cost?

## Slide 12: Advantages of PERT/CPM
Especially useful when scheduling and controlling large projects
Straightforward concept and not mathematically complex
Graphical networks help to perceive relationships among project activities
Critical path and slack time analyses help pinpoint activities that need to be closely watched

## Slide 13: Advantages of PERT/CPM
Project documentation and graphics point out who is responsible for various activities
Applicable to a wide variety of projects
Useful in monitoring not only schedules but costs as well

## Slide 14: Limitations of PERT/CPM
Project activities have to be clearly defined, independent, and stable in their relationships
Precedence relationships must be specified and networked together
Time estimates tend to be subjective and are subject to fudging by managers
There is an inherent danger of too much emphasis being placed on the longest, or critical, path